## Sheet1
Id	Est. Difficulty	Feature Name	Est. Time
1	Simple	AddressTaken Analysis	½ – 1 Week
2	Simple	Collection of addresses in program memory	Done
3	Medium	Analysis of the runtime linker (libld)
4	Medium	CallTarget Analysis (I)	2 Weeks
5	Simple	Collection of CallTargets	Done
6	Medium	Identification of the expected parameter count
7	Medium	Pathwise forward function CFG liveness analysis
8	Simple	Merging of Paths
9	Medium	Relative CallSite Analysis (I)	2 Weeks
10	Simple	Collection of relative CallSites	Done
11	Medium	Identification of the provided parameter count
12	Medium	Pathwise backward function CFG liveness analysis
13	Simple	Merging of Paths
14	Medium	Binary Patching	½ – 1 Week
15	Medium	CallTarget tags
16	Simple	Tag-based CallSite vs CallTarget checks (generic!)
17	Simple	Scrambling unused register values (methodology!)
18	Simple	Verification: Dynainst vs Ground Truth (llvm)	1 Day
19	Simple	Parameter count
20	Medium	CallTarget Analysis (II)	2 Weeks
21	Medium	Identification of the provided return type
22	Medium	type ::= provides | does not provide
23	Medium	Relative CallSite Analysis (II)	2 Weeks
24	Medium	Identification of the expected return type
25	Medium	type ::= expects | does not expect
26	Simple	Verification: Dyninst vs Ground Truth (llvm)	1 Day
27	Simple	Return type (void | non-void)
28	High	CallTarget Analysis (III)	4 Weeks
29	High	Identification of the expected parameter types
30	Medium	Dyninst-based analysis
31	Medium	SmartDec (based on IdaPro) based, see the TypeAnalyser.cpp
32	Medium	see Section TypeReconstruction (pg. 14) in SmartDec.pdf
33	High	BAP-based analysis, this basically does the same but on BIL IR
34	High	Relative CallSite Analysis (III)	4 Weeks
35	High	Identification of the provided parameter types
36	Medium	Dyninst-based analysis
37	Medium	SmartDec (based on IdaPro) based, see the TypeAnalyser.cpp
38	Medium	see Section TypeReconstruction (pg. 14) in SmartDec.pdf
39	High	BAP-based analysis, this basically does the same but on BIL IR
40	Simple	Verification: Dyninst vs BAP vs Ground Truth (llvm)	1 Day – 2 Days
41	Simple	Parameter Type (int, float, pointer, …)	Done Paul
42	Simple	Return Type (void, int, float, pointer, …)	see comment in .ods file
43	Medium	AddressTaken Analysis (II)	1 – 2 Weeks
44	Medium	Vtable Identification
45	Medium	CallTarget Analysis (IV)	1 – 2 Weeks
46	Medium	Identification of VcallTargets
47	Medium	Relative CallSite Analysis (IV)	1 – 2 Weeks
48	Medium	Identification of VcallSites
49	Medium	Pattern-matching based approach
50	Simple	Verification: Implementatin vs Ground Truth (llvm)	1 Day
51	Simple	Vtable Identification, We will get also the code from Victor
52		in June, I just have to send an email to him again,
53		or we ask victor which exact versions of the servers he used (ID and date,
54		and we use the same ones)