## Sheet1
Id	Est. Difficulty	Feature Name	Est. Time
1	Simple	AddressTaken Analysis	½ – 1 Week
2	Simple	Collection of addresses in program memory	Done
3	Medium	Analysis of the runtime linker (libld)
4	Medium	CallTarget Analysis (I)	2 Weeks
5	Simple	Collection of CallTargets	Done
6	Medium	Identification of the expected parameter count
7	Medium	Pathwise forward function CFG liveness analysis
8	Simple	Merging of Paths
9	Medium	Relative CallSite Analysis (I)	2 Weeks
10	Simple	Collection of relative CallSites	Done
11	Medium	Identification of the provided parameter count
12	Medium	Pathwise backward function CFG liveness analysis
13	Simple	Merging of Paths
14	Medium	Binary Patching	½ – 1 Week
15	Medium	CallTarget tags
16	Simple	Tag-based CallSite vs CallTarget checks (generic!)
17	Simple	Scrambling unused register values (methodology!)
18	Simple	Verification: Dynainst vs Ground Truth (llvm)	1 Day
19	Simple	Parameter count
20	Medium	CallTarget Analysis (II)	2 Weeks
21	Medium	Identification of the provided return type
22	Medium	type ::= provides | does not provide
23	Medium	CallSite Analysis (II)	2 Weeks
24	Medium	Identification of the expected return type
25	Medium	type ::= expects | does not expect
26	Simple	Verification: Dyninst vs Ground Truth (llvm)	1 Day
27	Simple	Return type (void | non-void)
28	High	CallTarget Analysis (III)	4 Weeks
29	High	Identification of the expected parameter types
30	Medium	Dyninst-based analysis
31	High	BAP-based analysis
32	High	Relative CallSite Analysis (III)	4 Weeks
33	High	Identification of the provided parameter types
34	Medium	Dyninst-based analysis
35	High	BAP-based analysis
36	Simple	Verification: Dyninst vs BAP vs Ground Truth (llvm)	1 Day – 2 Days
37	Simple	Parameter Type (int, float, pointer, …)	Done Paul
38	Simple	Return Type (void, int, float, pointer, …)	see comment in .ods file
39	TODO	SmartDec (implement the same fixed point algorithm see SmartDec Paper)	TODO
40		see git repo folder MA_Binary_Variable Type_Reconstrction	see comment in .ods file
41	TODO	IDA Pro (as above)	TODO
42		see git repo folder MA_Binary_Variable Type_Reconstrction and IDA API	see comment in .ods file
43	TODO	angr tool (as above, everything in place but has this feature not)	TODO
44		see git repo folder MA_Binary_Variable Type_Reconstrction and angr API	see comment in .ods file
45	TODO	PIN (I do not know)	TODO
46		see git repo folder MA_Binary_Variable Type_Reconstrction and PIN API	see comment in .ods file
47	TODO	Other candiate TOOL and/or Algorithms, Please add	TODO
48		add commnet	see comment in .ods file
49	Medium	AddressTaken Analysis (II)	1 – 2 Weeks
50	Medium	Vtable Identification
51	Medium	CallTarget Analysis (IV)	1 – 2 Weeks
52	Medium	Identification of VcallTargets
53	Medium	Relative CallSite Analysis (IV)	1 – 2 Weeks
54	Medium	Identification of VcallSites
55	Medium	Pattern-matching based approach
56	Simple	Verification: Implementatin vs Ground Truth (llvm)	1 Day
57	Simple	Vtable Identification, We will get also the code from Victor
58		in June, I just have to send an email to him again,
59		or we ask victor which exact versions of the servers he used (ID and date,
60		and we use the same ones)